## Sheet1
|  | Comments | Recommendation | Status
TEST.PD.PHY.ALL.02 | Eye parameter |  |  | 0410Jeff: this item GRL can add note "using GRL C2EPR tester pass", so we can focus on other item. Jeff: Sangean trying to provide partial of CC layout since they have concern about provide all layout file. Will provide it later. And they get feedback from GRL side information said PD controller can adjust some parameter to fix eye parameter issue. But I didn't find any register about this. Do you have any idea? Or it should relative with HW layout?
TEST.PD.PROT.SRC.08 VCONN Swap | The UUT did not send a Hard Reset signal after the max of tVCONNSourceOn in the PD2 mode. | tVCONN Source on = 50ms Need to check on EVM, seeing 188ms in customer lgos | Reviewed log, potential FW issue, checking with team 0410 No feedback from FW yet. Will update when I hear back. | Jeff: We have get the customer board, we can ship one board to you for clarify the issue. Please send me your shipping address.
TEST.PD.PS.SRC.01 | The UUT VBUS voltage was not within the limits of vSrcNew or vPpsNew or vAvsNew. | Is PP5V being powered during this time? Does the PD have power?Please share schematic. | Issue with power path and IR drop, may be able to do some changes with some offset, but need to be careful | 0410Jeff: Seem we have modified source to PP3(BQ25792 to cause IR drop). External 5V have load compensation, we will modified it to PP1(External 5V) Jeff: Should be yes. How do I know PP5V powered in this time? I mean how to test this function? Is it source PDO1 5V/3A power? I've passed shcematic via E2E.
TEST.PD.PS.SNK.01 |  | Need to retest, For some reason it is requesting .75 for 20-V instead of 1-A | The customer has "Autonegotiate Sink 0x37", Auto Compute Sink Min Power set to Host controlled. Why did they set this? It seems to affect this test. To fix this test, set this field to "PD Controller will compute" After I changed this, test still failed, but now seems to be a tester issue. Says that PDO not in VIF, but 20-V/1-A is in the VIF 0410 I'm not sure what the PS.SRC.03 issue was. Jeff, can you share the origianl failure for PD.PS.SRC.03, or swap the field I mentioned and retest to see if the failure is still there? | 0410Jeff: GRL reply this is tester issue. Jeff:Here is the comment from Raymond. 2. For TEST.PD.PS.SRC.03, if the test fails again you can try updating the JSON configuration in Autonegotiate Sink register (0x37) to configure TPS25751 to automatically disable PPHV if the source/tester isn’t able to provide a certain power threshold (Capability mismatch). You’ll need to set these settings below: a. No Capability Mismatch [3] set to 0x0 (The capability mismatch bit will be asserted to indicate to the attached source that more power is desired) b. Auto Disable Sink Upon Capability Mismatch [6] set to 0x1 (enabled) c. Auto Neg Capabilities Mismatch Power [61:52] set to low power (i.e. 250mW).
COMMON.CHECK.PD.3 -Test.PD.PS.SNK.2 | The UUT did not respond to the Tester message with a right GoodCRC. | Need to check in lab Replicated, debugging | Bigger Issue wit SNK.2, 5-V is getting lost when sourcing Pending See PD.PS.SNK.2 tab
COMMON.CHECK.PD.3 -TEST.PD.PHY.PORT.1 | The UUT did not respond to the Tester message with a right GoodCRC. | Looks like a tester issue, see CommonPhyPort Sheet | Tester Issue
COMMON.CHECK.PD.5 -TEST.PD.PS.SNK.2 -Test.pd.ps.src.5 | The UUT was not allowed to send Hard_Reset signal./The UUT unexpectedly performs an Error Recovery. | Need to check in lab Replicated, debugging | See PD.PS.SNK.2 tab
Common.check.pd.5 -Test.pd.prot.src.10 |  | Test seems to be fine
COMMON.CHECK.PD.7 | In a Fixed PDO in a Source Capabilities message, bits B21:B20 (Peak Power) did not match the vendor value. | Peak Current in VIF and .json don't match. | VIF: PD Source->Source PDOs 2 and 3 JSON: Transmit Source Capabilities PDO 2 and 3 Decide which peak current setting you want for these PDOs, make sure it matches in VIF and JSON | Jeff: I've modified it and make it match.
COMMON.CHECK.PD.12.1 | In a Fixed PDO in the Sink Capabilities message, the current represented by bits B9:B0 did not match the vendor value. | PDO2 current does not match between VIF and JSON | VIF: PD Sink->Sink PDO 2 current is 2200mA JSON: transmit Sink Capabilities-> Sink_PDO2 current is 2.22-A (2220mA) Determine which you want and modify the VIF/JSON appropriately, make sure they match. | Jeff: I've modified it and make it match.
COMMON.CHECK.PD.14 -Test.pd.ps.snk.2 |  | Checking with team | See PD.PS.SNK.2 tab
COMMON.PROC.PD.7 | The UUT should have not sent a Discover Identity/SVIDs Request message when Attempts_Discov_SOP = NO. | Does the customer want to support this bit? If yes, just enable in VIF (PD capabilities) Customer: What is this for? TI: When we are a DFP, we can send a discover ID message. It's mainly if they are doing data and alt modes, or want VID/PID info from a far end device. If they don't need any of this (which is likely the case), I can try disabling it. If they want it, they need to change the "Attempts_DISCOV_SOP" VIF field. | Waiting customer response | Jeff: I've modified VIF Attempts_Discov_SOP = YES.

## CommonPhyPort
We are under tTrnasmit and the GoodCRC is being sent

## TEST.PD.PS.SRC.1
Issue is VBUS Drops too low when high current drawn
Customer may need to check with DC-DC team to see if there is a way to improve this behavior (better sensing)

## TEST.PD.PS.SNK2
This test seems to be causing failures because it is not executing
We send the PSRDY after
Customer Log | TI Log
For some reason, customers does not send the Source caps message after (Packet 179 in TI log). Can you ask the customer to test a power role swap with their board and see if it works?
Might need the I2C between the BQ and the PD controller. I tested with just the EVM and it seemed to be fine. EVM only has PP5V, no PPHV, so I'm a little surprised it was an issue on their boards.
Tested with same json, but just the EVM