## TI
Items | Date | Meeting minutes | target data | Owner | status | Remark
2024-9-09 Meeting
1 | 2024-09-09 | 1） TDA4XVL,TDA4AL的 AVL list： 1） 含Memory；2）含Sensor； [TI comments]I already send LDDR4 and eMMC support AVL question in TDA4AL-Q1 in TI E2E, waiting TI reply; [FIH comment] --> A sample follow EVM design, but still need Memory AVL | 2024-09-11 | Victor | close | 【0914 Victor】：参考EVN 上的型号。 4GB LPDDR4-4266 MT53D1024M32D4DT-046，OSPI Flash 8b,512Mb，MT35XU512ABA1G12，eMMC Flash MTFC16GAPALBH；目前可以收尋到的只有這些，有請TI提供
2 | 2024-09-09 | 2）TDA4AL 是否支持2 颗8MP的camera； [TI comment] -->Will need to check on this. It seems single 8MP camera has been tested before, but 2 8MP cameras we have not. List of cameras supported are here: https://software-dl.ti.com/jacinto7/esd/processor-sdk-rtos-j721s2/10_00_00_05/exports/docs/vision_apps/docs/user_guide/group_apps_basic_demos_app_single_cam.html. [TI Comments] 10.Will need to check on this. It seems single 8MP camera has been tested before, but 2 8MP cameras we have not. List of cameras supported are here: https://software-dl.ti.com/jacinto7/esd/processor-sdk-rtos-j721s2/10_00_00_05/exports/docs/vision_apps/docs/user_guide/group_apps_basic_demos_app_single_cam.html. It looks like 2x 8MP camera is possible. [FIH comments -Louis] 8MP is possible, but resolution or frame may reduced | 2024-09-11 | Victor | close
3 | 2024-09-09 | 3）DP 转CSI 芯片推荐成熟产品型号。 [TI comments] | 2024-09-11 | Victor | close | 0914 Clear：已采用lontium型号 0914 Victor ：上次開會了解如果只需要制具可以上淘寶買這片板子
4 | 2024-09-09 | 4）Power 架构设计和thermal 管理，请TI 另外会议讨论；请Shawn 帮忙预约TI Jim。 [TI comments]We provide PDN in the SCH file that is also zipped in the "Design files" section of the EVM product page. Thermal model is provided here: https://e2e.ti.com/support/processors-group/processors/f/processors-forum/1218112/tda4vl-q1-thermal-model-tzr-or-excml-format | 2024-09-11 | Shawn | close
5 | 2024-09-09 | 5）5套 EVM 开发套件 请免费提供；2sets--for SW，MD--Steve 2sets，1sets-HW | 2024-09-11 | Victor | close | 0914 Clear：：shawn 回复全部需要下PO
6 | 2024-09-09 | 6）Sony IMS728 sensor 是否可用，目前未包含在SDK 内，何时可用。（新增问题） [TI comments ] For RTOS, no. This will be needed to be developed by user-end. Sensors supported in RTOS SDK are here: https://software-dl.ti.com/jacinto7/esd/processor-sdk-rtos-j721s2/10_00_00_05/exports/docs/vision_apps/docs/user_guide/group_apps_basic_demos_app_single_cam.html. | 2024-09-11 | Victor | close
7 | 2024-09-09 | 7）请帮忙分享演算法整合的指导文件。（SW） [TI Comments]Vision apps will be the best location to start: https://software-dl.ti.com/jacinto7/esd/processor-sdk-rtos-j721s2/10_00_00_05/exports/docs/vision_apps/docs/user_guide/index.html | 2024-09-11 | Victor | close
8 | 2024-09-09 | TDA4AL-Q1 Debug port and programming, is the JTAG of MCU domain shared with SoC? [TI Comments] Please reference: https://e2e.ti.com/support/processors-group/processors/f/processors-forum/982443/tda4vm-mcu-island-and-main-can-be-debuged-by-only-one-jtag-interface |  |  | close
9 | 2024-09-09 | Please help provide an introduction to the overall SW architecture of TDA4AL-Q1 SoC and MCU. [TI COMMENTS] I would recommend reading the vision apps documentation as a start: https://software-dl.ti.com/jacinto7/esd/processor-sdk-rtos-j721s2/10_00_00_05/exports/docs/vision_apps/docs/user_guide/index.html The Linux SDK documentation and RTOS SDK documentation (vision apps is part of RTOS SDK) are also very good to know. Each of the documentation can be accessed here: https://www.ti.com/tool/PROCESSOR-SDK-J721S2. They are under "Download options"->"Documentation"->"SDK Documentation". |  |  | close
2024-9-11 Meeting
1 | 2024-09-11 | 1） 请帮忙推荐 ASIL D的DCDC，将用于第一级电源输入 [TI Jim comments]=> 目前帶ASIl DCDC 還在開發中, 建議可以參考公版使用LM5140 2 phase 或是LM5141 1phase 搭配voltage monitor. LM5141-q1 有符合Functional Safety-Capable [FIH comment] final selection LM5141&LM5143 |  |  | close
2 | 2024-09-11 | 2） 功耗表的填写，可以以我为 contact window。 13691358661 |  |  | close
3 | 2024-09-11 | 3） SW, MCALL 相关资料需要找TI 另行申请， @ Lance 知悉。 |  |  | close
4 | 2024-09-11 | 4） PMIC 供电目前并非独立分开供电给MCU 和SOC ，是否影响ASIL D？ AP: Jim |  |  | open
5 | 2024-09-11 | 5） 目前我们参考的是双DDR 参考设计， 功耗考虑上恐有不同。请问是否有单DDR的EVM 参考设计颗分享给我们 [FIH comment] SOC 支持单DDR， 本条close ， A sample Follw EVM design |  |  | close
2024-9-14 new add questions to TI
1 | 2024-09-14 | 1) 请TI 确认是否需要额外的 SW Code 开启 硬件HSM； 2）规格书第243 页提到的Y 码 应选哪一位才符合ASIL B的要求？ Y =G/C/0/5/R/D/P? 当前SOM EVM 内完整料号为 TDA4AL88TGAALZRQ1。 | 2024-09-17 | Victor | Open | 【0919： Victor】:這部分我有發在TI E2E 但目前還沒回覆
2 | 2024-09-14 | Main domain跟MCU domain的JTEG是否支持boundary scan? | 2024-09-17 | Victor | Open | Victor 已向TI 提问，待TI 回复。
3 | 2024-09-18 | 请TI 确认TDA4AL 是否支持以下 DPI 格式输出格式： 24-bit RGB, 或24-bit YcbCr。具体如附件。 | ASAP | Victor | Open | 【0919Victor】：這個部份我查了一下，目前看起來因該是軟體部分調整，可參考以下解釋 https://netwalk.blog.csdn.net/article/details/140698698?spm=1001.2101.3001.6650.2&utm_medium=distribute.pc_relevant.none-task-blog-2%7Edefault%7EYuanLiJiHua%7EPosition-2-140698698-blog-108991909.235%5Ev43%5Epc_blog_bottom_relevance_base4&depth_1-utm_source=distribute.pc_relevant.none-task-blog-2%7Edefault%7EYuanLiJiHua%7EPosition-2-140698698-blog-108991909.235%5Ev43%5Epc_blog_bottom_relevance_base4&utm_relevant_index=5&ydreferer=aHR0cHM6Ly9ibG9nLmNzZG4ubmV0L3hpYW9wZWlfeWFuL2FydGljbGUvZGV0YWlscy8xMDg5OTE5MDk%3D
4 | 2024-09-18 | 请提供LM5137F-Q1 规格书，属于secure sorce 。 |  | Victor | close | 【0919Victor】：這顆我目前也沒找到我只有找到LM5137-Q1，相關的資料可能要請TI提供 [0924 Clear] JIM 已提供
5 | 2024-09-18 | EVM 验证的memory 是4GB LPDDR 还是8GB LPDDR 还是both？ |  | Victor | close | 【0919Victor】：如果您是看這份PROC118E4(001)_BOM表格是使用MT53E2G32D4DT-046，就我所理解，只要是TI提供的線路圖上的MICRON LPDDR4不管容量多少，TI都會有這些LPDDR4的參數，謝謝。 [0925 Clear] Demo 板folow 参考设计BOM
6 | 2024-09-18 | LDO 类器件如下无功能安全认证的，是否可以提供FIT/ FTA/FMDEA 等参数？ |  | Victor | ongoing | 【0919Victor】：這部分我請我們家的FAE Jim協助。有AEC-Q100的物料理论上可以找到对应的参数，需要和TI 确认如何申请获得这些文档。
|  | TPS22965NDSGR |  | Victor | close | [0920 Clear]已下载
|  | TLV7103318QDSERQ1 |  | Victor | Open | [0924 Jim ] TLV710-Q1 & TLV733P-Q1 已申請FMA/FMD 文件, 預計4~5周才會下
|  | TLV73333PQDRVRQ1 |  | Victor | close | [0925 Clear] JIM 已提供已提供TLV733P-Q1 FMD
|  | TLV73318PQDRVRQ1 |  | Victor | close | [0925 Clear] JIM 已提供 已提供TLV733P-Q1 FMD
|  | SN74LVC2G66QDCURQ1 |  | Victor | close | [0920 Clear]已下载
7 | 2024-09-25 | 功耗初版发FB-TK ，请TI review |  | VICTOR&JIM | Open | 【0925 Baoyuan】功耗表格已评估，待TI review
8 | 2024-09-25 | TAD4AL CSI TX 转FPDLINK 将采用TI DS90UB971RHBTQ1, 是否适用， 如频宽等是否匹配？ |  | Victor | Open